# Robust Monocular Visual Odometry for Agile UAVs

Failure Characterization and Recovery in Simulation — Research Project Plan

Purab Sen · Simulation-only (ROS2 / Gazebo / PX4) · Target: ETH SSRF, Robotics area

# Goal

Produce evidence of genuine research capability — a real question, a controlled experiment, honest results — not just a working demo. The project is designed to stand on its own: it becomes Hovr's perception layer and a reusable failure-detection module regardless of any single application's outcome.

# Research Question

How does monocular visual odometry degrade under increasingly aggressive UAV motion, and can a lightweight motion-aware failure-detection mechanism predict impending tracking failure early enough to enable useful recovery?

Hypothesis: as angular velocity and image-space feature velocity increase, feature-track survival decreases and VO drift increases; a motion-aware detector can identify impending tracking failure before complete loss and reduce recovery time.

Falsifiability check — if the intervention doesn't improve VO, the project still produces: a quantified characterization of how motion severity and observable image-quality signals relate to VO failure, including which conditions predict it and which don't. The experiment has value independent of whether the intervention wins.

# Design Principles (from review)

- Treat the VO estimator as swappable infrastructure — the research question survives even if the underlying algorithm changes.

- Quantify motion severity numerically (velocity, angular velocity, acceleration, image-space feature velocity) — never subjective labels like "aggressive."

- Keep the project singular. No merged side-projects (chassis generation, GLaDOS arm) — those live in the personal statement as future directions only.

- Pre-register the hypothesis before running the full experiment, so the intervention isn't tuned post-hoc to fit observed failures.

- Report mean ± std / confidence intervals across repeated trials — never a single RMSE number.

- Solve monocular scale alignment explicitly before computing ATE — an unaligned comparison is mathematically meaningless.

- PX4 stays boring: it is the trajectory generator, not the research subject.

# Phase 0 — Infrastructure (hard gate, no research yet)

Exit condition: given one fixed PX4 trajectory and one fixed configuration, a single documented command sequence reproduces synchronized camera + ground-truth data, runs VO, aligns the trajectory, and generates the estimated-vs-ground-truth plot — from a clean workspace. The plot can be ugly. The pipeline cannot be mysterious.

## 0A — Sensor + Ground Truth

- Confirm Gazebo camera topic; document encoding, resolution, frame rate

- Extract and save camera intrinsics and distortion parameters

- Confirm camera frame convention (forward/up/right)

- Build a recorder: save frames + timestamps to disk

- Confirm ground-truth pose topic; static sanity test (stationary, stable readings)

- Motion sanity test: move drone in one known direction, confirm ground truth agrees

- Document coordinate convention (NED/ENU, quaternion order) explicitly

## 0B — Synchronization

- Record camera + ground truth simultaneously on a fixed trajectory

- Compute measured timestamp association (not arrival-order matching)

- Output diagnostic: frame count, pose count, matched pairs, max/median timestamp gap

- Set and document an acceptable tolerance

## 0C — Minimal VO

- Implement: feature detection → matching → essential matrix → relative pose → trajectory integration

- No IMU, no loop closure, no neural nets, no recovery logic yet

- Log intermediate quantities from day one: feature counts, inlier ratios, per-frame relative motion

- Run on a boring fixed trajectory (straight line + gentle turn)

## 0D — Alignment + Evaluation

- Implement scale/trajectory alignment (e.g. via evo) before computing any error metric

- Build pipeline: raw VO trajectory → alignment → ATE/RPE → plot

- Confirm this runs end-to-end automatically on 0C output

## 0E — Reproducibility Gate

- Freeze environment: exact OS/ROS2/Gazebo/PX4/Python/package versions documented

- Commit PX4/Gazebo config + trajectory script to Git

- One command/documented sequence reproduces the full pipeline from a clean workspace

- Start the failure log (date / problem / hypothesis / change / result / learning)

## Phase 0 Final Exit Checklist

- Camera stream reproducible

- Ground truth reproducible

- Timestamp association measured

- Coordinate frames understood and documented

- Fixed trajectory replayable

- VO produces a trajectory

- Scale alignment works

- ATE/RPE computed automatically

- Plot generated automatically

- Workspace could be deleted and rebuilt from documentation alone

# Phase 1 — Baseline Characterization

Goal: understand exactly how and when the baseline fails, before any intervention is designed.

- Define motion severity quantitatively: velocity, angular velocity, acceleration, image-space feature velocity — as numeric ranges, not labels

- Build a trajectory generator producing controlled severity levels (e.g. low / medium / high / extreme, each numerically defined)

- Run baseline VO across the full severity matrix, multiple repeated trials per condition

- Compute ATE, RPE, tracking-loss rate — mean ± std across trials, not single numbers

- Output: a failure map — which conditions break the baseline, and how

- Important: you may discover your planned intervention doesn't target the dominant failure mode. That's a valid, useful finding — let Phase 1 data inform Phase 2, don't lock the intervention in advance

# Phase 2 — Hypothesis and Intervention

Goal: design a failure-prediction mechanism informed by Phase 1 data, not designed in advance and tuned to fit results.

- Identify candidate precursor signals from Phase 1 (feature-track survival, image-space feature velocity, inlier ratio trends, etc.)

- Build a lightweight failure-prediction mechanism — predict impending failure, not just detect it after the fact

- Define the recovery action it triggers

- Write down the hypothesis and expected outcome before running the full experiment (pre-registration) — this is what keeps the result falsifiable rather than post-hoc

# Phase 3 — Full Experiment

Goal: run the clean baseline-vs-intervention comparison.

- Same severity matrix and repeated-trial structure as Phase 1, now comparing baseline vs. intervention

- Metrics: ATE, RPE, tracking-loss rate, recovery time, drift/meter, prediction lead time

- Automate data collection and plotting — no manual curation of results

- Report failure-conditioned results (metrics broken out by severity level), not just aggregate numbers

# Phase 4 — Analysis and Writeup

Goal: turn results into an honest research narrative.

- Analyze where the intervention helped, where it didn't, and why

- 2–4 page report: research question → hypothesis → method → experimental design → results → failure analysis → limitations → conclusion

- Explicitly scope claims to simulation: "we characterize degradation under controlled simulated conditions," not "we solve robust VO for agile drones"

- Clean, reproducible GitHub repo: README, research_question.md, methodology.md, src/, configs/, experiments/, results/, plots/, report.pdf

# Downstream Value (independent of SSRF outcome)

- Hovr: becomes the drone's actual perception/localization layer, replacing reliance on sim ground truth

- GLaDOS arm: the failure-detection concept (predict degraded state estimation before full failure) transfers to any visual tracking on the arm

- Grad school portfolio: a documented research question with controlled experiments and honest results strengthens every future application, not only SSRF

- Personal skill floor: real understanding of visual geometry, pose estimation, and experimental design — durable regardless of any single outcome

# Personal Statement Framing

Narrative arc: AI/data science background → deliberate crossing into robotic perception → this project as the evidence of that transition. Not "I have robotics experience," but "I identified a perception problem and built the foundation to investigate it rigorously." Future directions (generative chassis design, GLaDOS arm) mentioned briefly as intellectual extensions, not built components.